## Change Order Tracker
CHANGE ORDER & COST IMPACT TRACKER
Track Change Order Cost & Schedule Impact by Status — Summit Tools (summittools.ai)
PROJECT INFORMATION
Project Name: |  |  |  |  | Job / Contract #:
Client: |  |  |  |  | Project Manager:
Original Contract Value ($): |  |  |  |  | Report Date:
COST IMPACT SUMMARY
Original Contract Value ($) |  | Total Approved COs ($) |  | Total Pending COs ($) |  | Revised Contract Value ($) |  | % Change from Original |  | Total Schedule Impact (Days)
|  | 12500 |  | 4200 | [5 empty] | 5
CHANGE ORDER LOG — Enter Each Change Order Below
CO # | Description | Category | Date Submitted | Requested By | Cost Impact ($) | Schedule Impact (Days) | Status | Date Approved | Approved By | Notes
CO-001 | Additional excavation for unforeseen rock formation | Unforeseen Condition | 2026-03-14 | Site Superintendent | 12500 | 5 | Approved | 2026-03-20 | Owner / PM | Approved with revised unit pricing
CO-002 | Upgrade lighting fixtures per updated energy code | Code Requirement | 2026-04-02 | Electrical Sub | 4200 | 0 | Pending |  |  | Awaiting owner decision
CO-003 | Relocate mechanical room per owner request | Owner Request | 2026-04-10 | Owner Representative | 8750 | 3 | Rejected | 2026-04-18 | Owner | Owner declined — cost prohibitive
TOTAL |  |  |  |  | 25450 | 8
Color Key: |  | Approved |  | Pending |  | Rejected |  | Sample row — replace with data
Change Order & Cost Impact Tracker — provided by Summit Tools (summittools.ai)

## Instructions
CHANGE ORDER & COST IMPACT TRACKER — USER GUIDE
What This Template Does
This workbook logs every change order on a job and rolls them up into a live summary of cost and schedule impact. It separates Approved, Pending, and Rejected change orders so you always know your true Revised Contract Value and how much cost exposure is still outstanding.
Getting Started
1. Fill in Project Information: Project Name, Client, Job/Contract #, Project Manager, Original Contract Value ($), and Report Date. 2. In the Change Order Log, replace the three sample rows (shaded yellow) with your own change orders, or delete them if not needed. 3. For each change order enter: CO #, Description, Category (pick from the dropdown), Date Submitted, Requested By, Cost Impact ($), Schedule Impact (Days), and Status (Pending, Approved, Rejected, or Approved w/ Revisions). 4. Once a change order is decided, fill in Date Approved, Approved By, and any Notes.
Reading the Cost Impact Summary
The six cards at the top roll up every row in the Change Order Log. Total Approved COs ($) and Total Schedule Impact (Days) include change orders marked Approved or Approved w/ Revisions. Total Pending COs ($) totals everything still marked Pending — this is your outstanding cost exposure. Revised Contract Value is your Original Contract Value plus Total Approved COs, and % Change from Original shows how far the approved change orders have moved the contract from its starting value.
Understanding the Status Colors
Approved and Approved w/ Revisions turn green and count toward your Revised Contract Value. Pending turns amber — these are submitted but undecided, and their cost sits outside your contract value until resolved. Rejected turns red and is excluded from every total, but stays in the log as a record that the change order was submitted and declined.
Tips
Update Status as soon as a decision is made so the summary cards stay accurate. Keep Cost Impact and Schedule Impact entered for every change order, even Rejected ones — it gives you a full record of what was proposed and helps with future estimating. Review Total Pending COs ($) regularly so you're not surprised by outstanding cost exposure at project close-out.