## Bid Comparison
SUB BID COMPARISON & LEVELING
Compare Subcontractor Bids by Price & Scope — Summit Tools (summittools.ai)
PROJECT INFORMATION
Project Name: |  |  |  |  | Trade / Scope:
Bid Due Date: |  |  |  |  | Estimator:
GC Budget / Estimate ($): |  |  |  |  | # of Bids Received: | 3
BID SUMMARY — Enter Each Subcontractor's Bid Below
Bidder / Company | Base Bid ($) | Bond & Insurance Provided? | Scope Gaps Found? | Adjustment for Missing Scope ($) | Inclusions / Exclusions / Clarification Notes | Adjusted Bid ($) | Rank | Recommend
Northline Contracting | 184500 | Yes | No | 0 | Clean bid — no exclusions noted | 184500 | 3
Baseline Grading Co. | 171200 | Yes | Yes | 8500 | Missing traffic control & dewatering — adjustment added by GC | 179700 | 1 | ✓ Best Value
Redstone Earthworks | 179900 | No | No | 0 | Bonding & insurance not confirmed — flag before award | 179900 | 2
Color Key: |  | Scope Gap Flagged |  | Bonding/Insurance Missing |  | Best Value (Rank 1)
Sub Bid Comparison & Leveling — provided by Summit Tools (summittools.ai)

## Scope Leveling
SCOPE LEVELING CHECKLIST
Confirm Every Bidder Included the Same Scope — Summit Tools (summittools.ai)
SCOPE LEVELING — Bidder Names Sync Automatically From Bid Comparison
Scope / Line Item | Northline Contracting | Baseline Grading Co. | Redstone Earthworks |  | # Included | Scope Gap Flag
Mobilization & Site Setup | Yes | Yes | Yes |  | 3 | Complete
Labor | Yes | Yes | Yes |  | 3 | Complete
Materials | Yes | Yes | Yes |  | 3 | Complete
Equipment & Tools Rental | Yes | Yes | Yes |  | 3 | Complete
Permits & Fees | Yes | Yes | Yes |  | 3 | Complete
Bonding & Insurance | Yes | Yes | No |  | 2 | Gap Found
Safety & Traffic Control | Yes | No | Yes |  | 2 | Gap Found
Waste / Debris Disposal | Yes | Yes | Yes |  | 3 | Complete
Warranty (1-Year Minimum) | Yes | Yes | Yes |  | 3 | Complete
Change Order Provision Included | Yes | Yes | Yes |  | 3 | Complete
Color Key: |  | Gap Found (scope missing) |  | Complete (all bidders included)
Scope Leveling Checklist — provided by Summit Tools (summittools.ai)

## Instructions
SUB BID COMPARISON & LEVELING — USER GUIDE
What This Template Does
This workbook helps you compare subcontractor bids apples-to-apples before you award a trade. The Bid Comparison tab ranks each bidder's adjusted price and flags missing bonding or scope gaps. The Scope Leveling tab is a line-item checklist that confirms every bidder actually included the same scope of work — so the lowest number isn't hiding an exclusion that will show up as a change order later.
Getting Started — Bid Comparison Tab
1. Fill in Project Information: Project Name, Trade/Scope, Bid Due Date, Estimator, and your GC Budget/Estimate ($). The # of Bids Received field counts automatically as you add bidder names. 2. In the Bid Summary table, replace the three sample rows (shaded yellow) with your own bidders, or delete them if not needed. 3. For each bidder enter: Base Bid ($), whether Bond & Insurance was provided (Yes/No dropdown), whether Scope Gaps were found (Yes/No dropdown), an Adjustment for Missing Scope ($) if you had to price in something they excluded, and any Inclusions/Exclusions/Clarification Notes. 4. Adjusted Bid ($), Rank, and Recommend calculate automatically — you don't need to touch those columns. Adjusted Bid = Base Bid + Adjustment for Missing Scope.
Interpreting Rank, Best Value & Scope Gap Flags
Rank ranks bidders by Adjusted Bid ($) from lowest (1) to highest — this accounts for any pricing adjustments, not just the raw base bid. Recommend shows a green "✓ Best Value" on the Rank 1 row. On the Bid Comparison tab, a bidder's Bond & Insurance answer turns bold red if marked "No" — confirm this before awarding. A "Yes" under Scope Gaps Found highlights amber as a reminder to review the adjustment and notes columns for that bidder.
How Scope Leveling Syncs With Bid Comparison
The six bidder-name columns on the Scope Leveling tab pull live from the Bidder/Company names you enter on the Bid Comparison tab — rename a bidder there and it updates here automatically. For each standard scope line item, mark Yes or No per bidder to record whether their bid included it. # Included counts how many bidders said Yes, and Scope Gap Flag shows "Gap Found" (red) if any bidder answered "No", or "Complete" (green) once everyone matches. Use the five blank rows at the bottom of the table to add scope items specific to your trade.
Tips Before Awarding the Trade
Don't award on price alone — check the Scope Leveling tab for any "Gap Found" rows before signing a contract. A bidder with a lower Adjusted Bid but multiple scope gaps can end up costing more once those gaps surface as change orders. Confirm bonding & insurance status directly with any bidder flagged red, and keep the Inclusions/Exclusions/Clarification Notes column detailed — it's your record of what each price actually includes if a dispute comes up later.